## Navarra CS
Interconnection | LARRAU |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | Navarra CS
Technical characteristics: |  | Km |  | D(") |  | P(MW) | 38
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | YES
|  | Winter | Summer
Spain-France (Common Value) : |  | 0
France-Spain (Common Value) : |  | Max: 100 Min: 50 (W)/ 40 (S)
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2009 |  |  | 2009-05-01
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | Apr-2004 |  |  | 2005-05-01
3.2 Environmental Assessment |  |  |  |  | 2007-06-01
3.3 Final (Authorisation for starting construction) |  | Dec-2006 |  |  | 2007-11-01
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 100% |  |  | 100%
4.2 Procurement |  | 100% |  |  | 100%
4.3 Construction |  | 100% |  |  | 100%
4.4 Commissioning |  | 100% |  |  | 100%
Causes of delays (if applied)
Comments

## Lemoa-Haro
Interconnection | Larrau |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | Pipeline Lemoa-Haro
Technical characteristics: |  | Km | 92 | D(") | 26 | P(MW)
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | YES
|  | Winter | Summer
Spain-France (Common Value) : |  | 0
France-Spain (Common Value) : |  | Max:100 Min: 30(W) / 20 (S)
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2009 |  |  | 2009-08-01
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | 2006-03-01 |  |  | Apr-2006
3.2 Environmental Assessment |  |  |  |  | 2007-09-01
3.3 Final (Authorisation for starting construction) |  | 2006-05-01 |  |  | Dec-2007
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 100% |  |  | 100%
4.2 Procurement |  | 100% |  |  | 100%
4.3 Construction |  | 100% |  |  | 100%
4.4 Commissioning |  | 100% |  |  | 100%
Causes of delays (if applied)
Comments

## Reinforcement of Haro CS
Interconnection | Larrau |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | Reinforcement of Haro CS
Technical characteristics: |  | Km |  | D(") |  | P(MW) | 23
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | Yes
|  | Winter | Summer
Spain-France (Common Value) : |  | 0
France-Spain (Common Value) : |  | Max:100 Min: 30(W) / 20 (S)
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2009 |  |  | 2009-08-01
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | 2006-03-01 |  |  | 2006-07-01
3.2 Environmental Assessment |  |  |  |  | apr-07
3.3 Final (Authorisation for starting construction) |  | 2006-09-01 |  |  | Dec-07
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 100% |  |  | 100%
4.2 Procurement |  | 100% |  |  | 100%
4.3 Construction |  | 100% |  |  | 100%
4.4 Commissioning |  | 100% |  |  | 100%
Causes of delays (if applied)
Comments

## Pipeline Castelnou-Tivisa
Interconnection | Larrau |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | Pipeline Castelnou – Tivisa (loop)
Technical characteristics: |  | Km | 91 | D(") | 26 | P(MW)
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | YES
|  | Winter | Summer
Spain-France (Common Value) : |  | 30(W) / 50 (S)
France-Spain (Common Value) : |  | 100
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2009 |  |  | Sep/Oct 2009
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | 2006-03-01 |  |  | 2007-02-01
3.2 Environmental Assessment |  | 2007-03-01 |  |  | Apr-09
3.3 Final (Authorisation for starting construction) |  | 2007-03-01 |  |  | 2009-10-01
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 100% |  |  | 100%
4.2 Procurement |  | 100% |  |  | 100%
4.3 Construction |  | 0% |  |  | 100%
4.4 Commissioning |  | 0% |  |  | 100%
Causes of delays (if applied)
Comments

## Villar de Arnedo CS
Interconnection | Larrau |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | Villar de Arnedo CS
Technical characteristics: |  | Km |  | D(") |  | P(MW) | 35
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | YES
|  | Winter | Summer
Spain-France (Common Value) : |  | 110(W) / 100 (S)
France-Spain (Common Value) : |  | 100
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2010 |  |  | 2011-02-01
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | apr-2006 |  |  | 2008-02-01
3.2 Environmental Assessment |  |  |  |  | 2008-11-01
3.3 Final (Authorisation for starting construction) |  | 2008-07-01 |  |  | 2010-03-01
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 81% |  |  | 100%
4.2 Procurement |  | 61% |  |  | 100%
4.3 Construction |  | 0% |  |  | 100%
4.4 Commissioning |  | 0% |  |  | 100%
Causes of delays (if applied)
Comments

## Pipeline Tivisa-Paterna
Interconnection | Larrau |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | Pipeline Tivisa Paterna (loop)
Technical characteristics: |  | Km | 235 | D(") | 40 | P(MW)
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | YES
|  | Winter | Summer
Spain-France (Common Value) : |  | 30(W) / 50 (S)
France-Spain (Common Value) : |  | 100
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2009 |  |  | 2011-11-01
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | 2006-03-01 |  |  | 2007-05-01
3.2 Environmental Assessment |  | 2007-06-01 |  |  | 2009-07-01
3.3 Final (Authorisation for starting construction) |  | 2007-06-01 |  |  | jan-11
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 100% |  |  | 100%
4.2 Procurement |  | 98% |  |  | 100%
4.3 Construction |  | 69% |  |  | 100%
4.4 Commissioning |  | 100% |  |  | 100%
Causes of delays (if applied)
The pipeline is divided in 3 tranches (i.e North, Central, South). The 3 tranches are already commissioned
Comments

## Pipeline Yela-Villar de Arnedo
Interconnection | Larrau |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | Pipeline Yela – Villar de Arnedo
Technical characteristics: |  | Km | 251 | D(") | 30 | P(MW)
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | YES
|  | Winter | Summer
Spain-France (Common Value) : |  | 110(W) / 100 (S)
France-Spain (Common Value) : |  | 100
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2010 |  |  | aug-2012
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | apr-2006 |  |  | 2008-06-01
3.2 Environmental Assessment |  | 2006-05-01 |  |  | 2010-11-01
3.3 Final (Authorisation for starting construction) |  | 2008-07-01 |  |  | Dec-10
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 100% |  |  | 100%
4.2 Procurement |  | 100% |  |  | 100%
4.3 Construction |  | 100% |  |  | 100%
4.4 Commissioning |  | 100% |  |  | 100%
Causes of delays (if applied)
Comments

## Pipeline Zarza de Tajo-Yela
Interconnection | Larrau |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | Pipeline Zarza de Tajo- Yela
Technical characteristics: |  | Km | 106 | D(") | 30 | P(MW)
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | YES
|  | Winter | Summer
Spain-France (Common Value) : |  | 110(W) / 100 (S)
France-Spain (Common Value) : |  | 100
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2010 |  |  | 4Q2013
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | Apr-2006 |  |  | Dec-2007
3.2 Environmental Assessment |  | Apr-2006 |  |  | 2011-11-01
3.3 Final (Authorisation for starting construction) |  | 2008-05-01 |  |  | Aug-2012
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 70% |  |  | 100%
4.2 Procurement |  | 95% |  |  | 100%
4.3 Construction |  | 0% |  |  | 92%
4.4 Commissioning |  | 0% |  |  | 0%
Causes of delays (if applied)
Comments |  | Final Authorisation for starting construction

## CS at the border
Interconnection | Biriatou |  | Review date: (dd/mm/yyyy): |  |  | 2013-11-06
1.1 Name of the infrastructure: |  | CS at the border |  |  |  |  | 2 (1+1) Electric Moto-Compressor, aprox. 5,5 MW each
Technical characteristics: |  | Km |  | D(") |  | P(MW)
1.2 Name of the responsible TSO: |  | Enagás S.A.
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | YES
|  | Winter | Summer
Spain-France (Common Value) : |  | 60
France-Spain (Common Value) : |  | 0
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2015 |  |  | 2015
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | 2008-06-01 |  |  | Apr-2013
3.2 Environmental Assessment |  | 2013-09-01
3.3 Final (Authorisation for starting construction) |  | 2013-10-01
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  | 0% |  |  | 10%
4.2 Procurement |  | 0% |  |  | 0%
4.3 Construction |  | 0% |  |  | 0%
4.4 Commissioning |  | 0% |  |  | 0%
Causes of delays (if applied)
Comments