## Chazelles compression
Interconnection | Compressor Station at Chazelles |  | Review date: (dd/mm/yyyy): |  |  | 2014-11-03
1.1 Name of the infrastructure: |  | Comressor station at Chazelles
Technical characteristics: |  | Km |  | D(") |  | P(MW) | 3x12,5
1.2 Name of the responsible TSO: |  | GRTgaz
1.3 Capacity with this infrastructure (GWh/day) |  |  |  | 1.4 Investment approved by TSO (YES/NO) |  |  | Yes
|  | Winter | Summer
Spain-France (Common Value) : |  | 175
France-Spain (Common Value) : |  | 70
|  | 2.1Initial Planning |  |  | 2.2 Updated forecast (according to real works status)
Starting operation date |  | 2013-04-01 |  |  | 2013-05-24
Administrative milestones |  | A) Application Date |  |  | B) Concession Date
3.1 Initial (promoter choice) |  | H2'07 |  |  | 2007-09-01
3.2 Environmental Assessment |  | 2009 |  |  | 2010-09-01
3.3 Final (Authorisation for starting construction) |  | 2010 |  |  | 2010-10-22
Project advance |  | A) In previous review (%) |  |  | B) Current (%)
4.1 Engineering |  |  |  |  | 100%
4.2 Procurement |  |  |  |  | 100%
4.3 Construction |  |  |  |  | 100%
4.4 Commissioning |  |  |  |  | 100%
Causes of delays (if applied) |  | technical issues on compressor
Comments