## Slide 1: SWE Day- Ahead market coupling
7 April 2014
Implementation Group meeting – Paris

## Slide 2: Project status
Status of tests for the Full Coupling Go-live
  Integration tests finalized successfully - All systems are operational
  Simulation tests showed successful results
      If needed, fine tuning of procedures will be performed in April
  NWE/SWE tests started beginning of April
  Member tests scheduled on 22 April
      Information was sent to the members
Status of NWE – SWE Day-Ahead Operational Agreement (DAOA) signature
  Terms of Reference of the DAOA had been approved by the NWE JSC (25th March) and SWE SC (26th March)
  The drafting of the DAOA has been launched and will be finalized by mid-April
  The signature process will then start
      Objective: signed hard copies of the DAOA by all parties by end of April.
The target date for the SWE Full Coupling Go-live is subject to the final validation of the SWE SC on 23 April 2014
      Communication towards the external stakeholders currently under preparation (press release)

## Slide 3: Planning of the DAOA
Terms of Reference of the DAOA had been approved by the NWE JSC (25th March) and SWE SC (26th March)
Target is to receive the signed hard copies copies of the DAOA by all parties by 30th April.
Should not all parties be able to comply with this challenging deadline, it has been proposed as a back up solution, the 10th of May as the deadline to receive scanned signed copies.
3
 | 3/2-7/3 | 10/3-14/3 | 17/3-21/3 | 24/3-28/3 | 31/3-4/4 | 7/4-11/4 | 14/4-18/4 | 21/4-25/4 | 28/4-2/5
NWE-SWE DAOA ToR |  |  |  |  |  |  |  |  | 
NWE-SWE DAOA |  |  |  |  |  |  |  |  | 
Drafting of ToR
First draft DAOA
25/3:
SC approval of ToR
18/4
SC approval of DAOA
Signatures
30/4
All signed copies received
Finalization DAOA
2/4-3/4:
NWE-SWE workshop
9/4
NWE-SWE joint meeting

## Slide 4: Regulatory evolutions
The High level Spanish regulation (CNMC circular) that establishes the methodology for the management of the international interconnections was approved by CNMC (12/03/2014) and published (BOE 17/03/2014).
IFE Rules 3.1 were approved by CRE (12/03/2014) and by CNMC (13/03/2014) and published by CNMC (19/03/2014)
Evolutions in MIBEL: on-going changes
  A public consultation was held in February by REE and another one was held in February by CNMC in the framework of the CCE (Electricity Advisory Council)
  Approval of the Spanish Operational Procedures is expected in April
Evolutions in France: on-going changes
  Public consultation was held during the period 17 March to 31 March
  Approval of full market coupling and French I/E rules is expected in April

## Slide 5: High level planning – SWE Full coupling
 |  | Dec | Jan | Feb | March | April | May | June | July | August
Operational activities |  |  |  |  |  |  |  |  |  | 
Testing activities |  |  |  |  |  |  |  |  |  | 
Regulatory evolutions |  |  |  |  |  |  |  |  |  | 
2014
Operators training
Procedures refinement
Version
07/04/2014
Integration testing
NWE test for SWE Start up solution
Successful testing
Auction rules evolution
Final Regulatory approvals (RTE Import/Export Rules + Spanish Operational procedures)
NWE / SWE tests
Go live
Prep
Today
REE Public consultation
NWE/SWE Task Force
Simulation tests
Member tests
SWE Full Coupling Go live window
Integration testing
Regulatory approval
IFE rules
2013
High level Spanish regulation approval
French Public consultation
Signed
contracts
CNMC Public consultation

## Slide 6: Fallback for SWE full coupling
In case decoupling occurs, the MIBEL Day Ahead market will run independent from the rest of the Day Ahead Markets.
  The full coupling is foreseen to be launched in May with Intraday allocation as a fallback transitory solution.
  Works for the implementation of Shadow auctions are being carried out in parallel. This implementation will require:
  Regulatory changes: following the request from CNMC and CRE during the 14th IG meeting, provisions for the execution of Shadow Auction will be included in the future extension of HAR for FR-ES with approval expected by November 2014.
      Go-live for LT 2015 products: December 2014
      Go-live for Shadow Auctions : March 2015
    Contractual updates
      CASC Service Level Agreement
      RTE-REE Cooperation Agreement
    IT developments, that will start after the SWE Full Coupling Go-live in May, followed by testing of the new information exchanges
    Communication plan towards Stakeholders before each Go-live
    Regulatory comfort for needed regulatory updates and cost recovery, when needed
Regarding the allocation of Day Ahead cross zonal capacity at the PT-ES interconnection, existing MIBEL market mechanisms will apply.
FR-ES Interconnection
PT-ES Interconnection

## Slide 7: High level planning – Shadow Auctions Implementation
 |  | April | May | June | July | August | Sep | Oct | Nov | Dec | Jan | Feb | March
HAR and other regulatory evolutions |  |  |  |  |  |  |  |  |  |  |  |  | 
Contractual framework |  |  |  |  |  |  |  |  |  |  |  |  | 
IT Development and Testing activities |  |  |  |  |  |  |  |  |  |  |  |  | 
Version
07/04/2014
CASC Service Level Agreement (SLA) for Shadow Auctions (SA) in SWE Region
Approval of Spanish O.P and MIBEL Market Rules (SA)
Preparation of request for comfort letter
IT Testing for SA
Integration of IFE in HAR (LT + Shadow Auctions)
Public consultation
IT Developments for SA mainly in REE
Submission for NRAs approval
2014
Submission of request for comfort letter
Adaptation of Spanish O.P and MIBEL Market Rules (SA)
Receipt of comfort letter
2015
Go-live Shadow
Auctions
Today
HAR Approval*
Public consultations
Submission for NRAs approval
SA SLA Signature
* Applicable for all LT products covering periods starting on the 1st January 2015 . RTE does not foresee any IT developments and testing for HAR. REE is analyzing IT developments and testing required for HAR.
Update of CASC Service Level Agreement (SLA) for LT in SWE Region (HAR)
IT adaptations for application of HAR*
IT Testing HAR adapt*
Adaptations of Implementation Guide for HAR and SA
Updated SLA Signature

## Slide 8
Back up slides

## Slide 9: Project status
Status of tests for the Full Coupling Go-live
  Integration tests finalized successfully - All systems are operational
    9 days of tests were scheduled with a fully interconnected test environment and all the final systems with the aim to:
      Test the automatic mode for all types of scenarios (normal day, clock changes, exceptional situations)
      Test in particular the connectivity between the systems of RTE, the TSO CS and EPEX
      Successful connectivity between RTE / TSO CS / EPEX
      Successful reception of the nomination by RTE from ECC
      Successful test of the CRDS system for the FR-ES border even though some final adjustments
  Simulation tests (Wednesday 26 February 2014 – 30 March 2014) showed successful results
    This phase consists in testing the SWE procedures that were finalized on February 24th.
    A particular attention was given to the respect of the timings.
  NWE/SWE tests started beginning of April (SWE parties took the lead of these common tests)
  Member tests scheduled on 22 April (Information was sent to the members)